## Agenda Sample
RETREAT PLANNING TEMPLATE
| SCHEDULED RETREAT DATE: | 2024-09-01
4 MONTHS BEFORE |  | 2024-05-04
Set the vision and takeaway
Determine the price per head
Determine planning accountabilities
Gather location options for venues
Gather location options for flights
3 MONTHS BEFORE |  | 2024-06-03
Fill in basic day-to-day agenda
Determine location
Create short list of venues
2 MONTHS BEFORE |  | 2024-07-03
Sign a venue contract
Announce retreat location ot the team
Design customized swag, if any
Order customized swag
Select guest speakers and sign a speaking contract
Curate "connect with who you serve" list and invite to speak with the team
Create offiical short list of extra activities and local restaurants
Outline internal presentations being given to the team
Survey team members on their flight/travel/food preferences
30 DAYS BEFORE |  | 2024-08-02
Purchase team flights
Set up reservations for restaurants and activities
Finalize presentations being given to the team
Finalize and review agenda
2 WEEKS BEFORE |  | 2024-08-18
Plan for nothing. Issues will come up on their own!